## Utilization
Utilization in December – 2017 (Project: Audio processing using OpenMax )
Name | Roles and Responsibilites | Utilization in % for project | Utilization in % for Training | Week 1 | Week 1 deliverable | Week 2 | Week 2 deliverable | Week 3 | Week 3 deliverable
Nitesh | 1) Understanding of Yocto project workflow. 2) Understand of layers, receipes for supported architectures in yocto. 3) Yocto building process for different architectures and bitbake work flow. 4)Build Kernel images for RPI using Yocto. 5)Build Kernel images for BeagleBone using Yocto. 6) Understanding of SD card patition. 7) Basic Shell scripting to automate yocto build for different architecture 8) Understanding of Booting sequence. | Linux commands knowledge = 50% Booting sequence = 60 % Sd card partition = 100% Yocto build for Beagle board = 50% Shell script for building Yocto= 60% | - | 1) Understanding of Yocto project workflow. 2) Understand of layers, receipes for supported architectures in yocto. 3) Yocto building process for different architectures and bitbake work flow. | 1] Detail documents of Yocto build for Rpi, Dragon board. | 1)Build Kernel images for RPI using Yocto. 2)Build Kernel images for BeagleBone using Yocto. 3) Understanding of SD card patition. 4) Basic Shell scripting to automate yocto build for different architecture 5) Understanding of Booting sequence. | 1) Yocto build for RPI. 2) Yocto build for BeagleBone. 3) Shell scripting to automate yocto build for different architecture. 4) Documentation of Shell scripting Steps. | 1) Understanding of Android build process. 2)Understanding of Basic Flow of OpenMax. 3) Play audio using ADB commands on Prebuild android image. 4)Uderstading to write test script to automation in open max using adb | 1) Android build process flow. 2) OpenMax working flow.

## Dev Project Plan
4A Camera Project Plan
|  |  | October | [7 empty] | November | [7 empty] | December
|  |  | Week 1 | Deliverables | week 2 | Deliverables | Week 3 | Deliverables | Week 4 | Deliverables | Week 1 | Deliverables | week 2 | Deliverables | Week 3 | Deliverables | Week 4 | Deliverables | Week 1 | Deliverables | week 2 | Deliverables | Week 3 | Deliverables | Week 4 | Deliverables
| WBS | Enginners Assigned: 11 Haranath Murali Dama Jignesh N Patel Divya Preethika ShashankArora Rakesh Bathini Yasir NL Swetha Huded Satheesh Pradeep Gopinath Shaikh Ishaque Mallikarjun | 1)Camera driver for RPI3. 2)Undestanding ISP | Camera Driver | 1)Understanding camera drivers 2)Understanding v4l2 driver | V4l2 Driver | 1)Understanding of V4L2 2)Understanding of ALSA | V4L2 & ALSA | 1)Integration of CSI camera with RP3 2)Video capture with CSI camera and using gstreamer or other app 3)LTP testing | Camera Feature, Gstreamer Test Suite | 1)Understanding Bringing up of Dragon board & Porting and integration | Understanding of Bringing up of Dragon board | 1)Bringing up of Dragon board 2)Porting and integration | Bringing up of Dragon board | 1)Understanding of gstreamer from hardware to application (use linux apps or write Android app) 2)Yocto Skills | Gstreamer & Yocto Skills | 1)Changing v4l2 reflashing using YOCTO 2)Changing ALSA reflashing using YOCTO | Changing V4L2 & ALSA through Yocto | 1)Understanding of HAL | Android HAL Understanding | 1)Customizing HAL in RP3 and reflashing using YOCTO | Customizing HAL in RP3 and reflashing using YOCTO | 1)LTP testing 2)Customizing dragon board HAL – V4l2 | Dragon board HAL – V4l2 | Customizing dragon board HAL – ALSA | HAL-ALSA On Dragonboard
| task 1 | 1)Understanding of Camera driver for RPI3. 2)Undestanding ISP
| task 2 | 1)Understanding of Camera driver for RPI3. 2)Understanding of V4L2 driver
| task 3 | 1)Understanding of V4L2 for RPI3. 2)Understanding of ALSA driver
| task 4 | 1)Integration of CSI camera with RP3 2)Video capture with CSI camera and using gstreamer or other app
| task 5 | LTP testing
Delivery | task 6 | Camera Feature, Gstreamer Test Suite
| task 7 | 1)Understanding of Dragon Board 2)Understanding of Board Bring Up Dragon Board
| task 8 | Understanding of gstreamer from hardware to application (use linux apps or write Android app)
Delivery | task 9 | Yocto Skills
| task 10 | Changing v4l2 reflashing using YOCTO
| task 11 | Changing ALSA reflashing using YOCTO
| task 12 | Android porting on RPI3
Delivery | task 13 | Understanding of Android HAL
| task 14 | Customizing HAL in RP3 and reflashing using YOCTO
| task 15 | LTP testing
| task 16 | Customizing dragon board HAL – V4l2
| task 17 | Customizing dragon board HAL – ALSA
Android Audio Processing Project
|  | Ashok L Mohd Pasha Shravya Kumbham Smruthi Ranjan | BSP of RP3 | Board Bring up | Build kernerl using Yocto | YOCTO training | BT audio integration with RP3 | GIT /Gerit | BT audio Integration | BT audio Integration | Understand gstreamer | Audio codec Test scripts | Integrate gstreamer on linux machine | gstreamer | Tracing the HAL | Porting on Intel | understand ALSA | gstremer plugins | Building with changes to ALSA |  | DSP Noise cancellation algorithms analysis | Small PoC with DSP Algorithms | Making changes to DSP and buiding |  | Fixing bugs | DSP modified Audio processing demo
[7 empty] | Playing BT audio over RP3 | Jenkins configurations | Integration testing | Python test scipts | study DSP |  | Testing BT audio with gsteamer | BT audio playing on gstremer | Understand kernel | Integrate gstremer on linux | Tracing the flow from ALSA to drivers |  | DSP noise cancellation algorithm study |  | Implementing noise cancellation algorithm | preparing Test plans | bug fixing | Limited working demo playing BT audio with changes to DSP | comparison testing of audio
[7 empty] | Submissions using GIT / Gerrit |  |  |  | preparing test data |  | Bug fixes |  | Porting on other boards | Android framerwork | making changes in the gstreamer plugins and writing new gstreamer plugins | [5 empty] | writing test scripts |  | cancellation of particular noise filter
[7 empty] | study Android framework | Android framework |  |  |  |  | playing BT audio with gstreamer |  | Integrate gstreamer on RP3 | [7 empty] | pyton automation
[13 empty] | Playing audio files |  | Integrate with Android
Open CV/CL Image processing Project
|  | Ashok Siva Kumar Ramya Bala Anjaneyulu Deepika Rathod Raja Vithal Sandeep Goud Sandeep Reddy | BSP of RP3 | Board Bring up | Build kernerl using Yocto | YOCTO training | I2c Writing camera driver | GIT /Gerit | Application and Driver Integration | BT audio Integration | Integrating Python image processing libraries to development environment | Running the image to detect and recognize face demo | Integrating EMGU CV | Detecting the geometric shapes | Implementing the photometric stereo algorithm | Testing face. Geometric and photometric relationship | Creating new c++ libraries (if possible) | Modular code libraries for c++ | Integrating the opencv/cl onto RP3 | prodcutise the code for demo over RP3 | Integrating the code onto client board
[7 empty] | Integrating camera to RP3 | Jenkins configurations | Taking picture, fixing bugs | Camera related Python scripts | Study of various Image processing libraries | writing test scripts | Detecting face for Geometric relationship algorithm | Connectivity to database | Running the python scripts and testing combination of Input Image / Face detection |  | creating new python packages | Modular code libraries for python | running the algorithms from conencted camera
[7 empty] | Submissions using GIT / Gerrit | Camera Driver testing | Modifying the Driver |  | Creating Face detection algorithm |  | Running test cases accordingly |  | using the existing algorithms to process and train the pictures
[7 empty] | study Android framework |  | Writing Test scripts |  | writing python extraction libraries |  | connectivity to data base MangoDB over cloud
[7 empty] | Camera Driver Testing |  | creating python scripts for the https://cloud.google.com/vision/ APIs integrate | createing environment setup | creating a GUI /UX in Django to process image |  | training algorithm to detect and process the pictures
[7 empty] | Study open cv algorithms | [5 empty] | storing the processed pictures with metadata for comparitive retrieval

## SkillsRating
| Haranath | Murali | Jignesh | Mallikarjun | Sateesh | Rakesh | Divya | Shashank | Swetha | Isaque | Yasir
Board bring up (RP3) | 8 | 5 | 8 | 8 | 6 | 6 | 7 | 8 | 8 | 7 | 7
YOCTO | 6 | 3 | 6 | 6 | 4 | 5 | 5 | 5 | 3 | 4 | 7
Integration of BT with RP3 | 8 | 6 | 6 | 8 | 5 | 4 | 4 | 6 | 7 | 3 | 6
Debugging and fixing BT issues | 7 | 4 | 7 | 7 | 6 | 4 | 5 | 6 | 7 | 3 | 4
Integration of gstreamer | 4 | 2 | 4 | 4 | 3 | 8 | 7 | 3 | 8 | 4 | 6
BT audio using gstreamer | 4 | 2 | 5 | 4 | 3 | 6 | 5 | 3 | 6 | 4 | 4
Gerrit server | 8 | 8 | 7 | 6 | 9 | 7 | 8 | 3 | 5 | 7 | 7
Scons | 2 | 7 | 0 | 3 | 3 | 5 | 7 | 3 | 3 | 7 | 6
Build and Integration | 5 | 8 | 4 | 5 | 7 | 7 | 8 | 5 | 4 | 7 | 6
Python scripts | 6 | 2 | 1 | 5 | 5 | 4 | 5 | 2 | 4 | 6 | 5
UDP streaming for wifi | 5 | 1 | 2 | 3 | 3 | 3 | 3 | 4 | 7 | 0 | 0
LTP testing | 4 | 0 | 4 | 4 | 4 | 4 | 1 | 4 | 1 | 2 | 4
Device drivers | 8 | 5 | 7 | 8 | 4 | 3 | 2 | 7 | 5 | 3 | 5
Test and bug fixing | 7 | 5 | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 6
Open source submission | NA | 5 | NA | NA | NA | 7 | NA |  | NA | NA | NA